中华人民共和国河北省审计厅

Hebei Provincial Audit Office of the People's Republic of China

审　计　报　告

Audit Report

冀审外报〔2020〕8号

HEBEI AUDIT REPORT〔2020〕NO. 8

项目名称：   亚洲开发银行贷款河北省养老服务体系建设项目

Project Name:  Hebei Elderly Care Development Project

Financed by the Asian Development Bank

贷 款 号：    3536-PRC

Loan No. :     3536-PRC

项目执行单位：河北省政府外债项目管理服务中心

Project Entity:   Hebei Provincial Government Foreign Debt

Project Management & Service Center

会计年度：     2019

Accounting Year:  2019

目   录

Contents

一、审计师意见	1

I. Auditor’s Opinion	3

二、财务报表及财务报表附注	5

Ⅱ. Financial Statements and Notes to the Financial Statements	5

（一）资金平衡表	5

i. Balance Sheet	5

（二）项目进度表	7

ii. Summary of Sources and Uses of Funds by Project Component	7

（三）贷款协定执行情况表	10

iii. Statement of Implementation of Loan Agreement	10

（四）专用账户报表	11

iv. Special Account Statement	11

（五）财务报表附注	13

v. Notes to the Financial Statements	16

三、审计发现的问题及建议	19

III. Audit Findings and Recommendations	20

一、审计师意见

审计师意见

河北省政府外债项目管理服务中心：

我们审计了亚洲开发银行贷款河北省养老服务体系建设项目2019年12月31日的资金平衡表及截至该日同年度的项目进度表、贷款协定执行情况表和专用账户报表等特定目的财务报表及财务报表附注（第5页至第18页）。

（一）项目执行单位及河北省财政厅对财务报表的责任

编制上述财务报表中的资金平衡表、项目进度表及贷款协定执行情况表是你中心的责任，编制专用账户报表是河北省财政厅的责任，这种责任包括：

1．按照中国的会计准则、会计制度和本项目贷款协定的要求编制项目财务报表，并使其实现公允反映；

2．设计、执行和维护必要的内部控制，以使项目财务报表不存在由于舞弊或错误而导致的重大错报。

（二）审计责任

我们的责任是在执行审计工作的基础上对财务报表发表审计意见。我们按照中国国家审计准则和国际审计准则的规定执行了审计工作，上述准则要求我们遵守审计职业要求，计划和执行审计工作以对项目财务报表是否不存在重大错报获取合理保证。

为获取有关财务报表金额和披露信息的有关证据，我们实施了必要的审计程序。我们运用职业判断选择审计程序，这些程序包括对由于舞弊或错误导致的财务报表重大错报风险的评估。在进行风险评估时，为了设计恰当的审计程序，我们考虑了与财务报表相关的内部控制，但目的并非对内部控制的有效性发表意见。审计工作还包括评价所选用会计政策的恰当性和作出会计估计的合理性，以及评价财务报表的总体列报。

我们相信，我们获取的审计证据是适当的、充分的，为发表审计意见提供了基础。

（三）审计意见

我们认为，第一段所列财务报表在所有重大方面按照中国的会计准则、会计制度和本项目贷款协定的要求编制，公允反映了亚洲开发银行贷款河北省养老服务体系建设项目2019年12月31日的财务状况及截至该日同年度的财务收支、项目执行和专用账户收支情况。

（四）其他事项

我们还审查了本期内报送给亚洲开发银行的第HB002号提款申请书及所附资料。我们认为，这些资料均符合贷款协议的要求，可以作为申请提款的依据。

本审计师意见之后，共同构成审计报告的还有两项内容：财务报表及财务报表附注和审计发现的问题及建议。

中华人民共和国河北省审计厅

2020年6月30日

地址：中国河北省石家庄市友谊南大街195号

邮政编码：050051

电话：86-311-88606354

传真：86-311-88606120

I. Auditor’s Opinion

Auditor’s Opinion

To Hebei Provincial Government Foreign Debt Project Management & Service Center

We have audited the special purpose financial statements (from page 5 to page 18) of Hebei Elderly Care Development Project Financed by the Asian Development Bank, which comprise the Balance Sheet as of December 31, 2019, the Summary of Sources and Uses of Funds by Project Component, the Statement of Implementation of Loan Agreement and the Special Account Statement for the year then ended, and Notes to the Financial Statements.

Project Entity and Hebei Provincial Finance Department's Responsibility for the Financial Statements

The preparation of the Balance Sheet, the Summary of Sources and Uses of Funds by Project Component and the Statement of Implementation of Loan Agreement is the responsibility of your entity, while the preparation of the Special Account Statement is the responsibility of Hebei Provincial Finance Department, which includes:

i. Preparing and fair presenting the accompanying financial statements in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement;

ii. Designing, implementing and maintaining necessary internal control to ensure that the financial statements are free from material misstatement, whether due to fraud or error.

Auditor’s Responsibility

Our responsibility is to express an opinion on these financial statements based on our audit. We conducted our audit in accordance with the Government Auditing Standards of the People’s Republic of China and International Standards on Auditing. Those standards require that we comply with ethical requirements and plan and perform the audit to obtain reasonable assurance about whether the financial statements are free from material misstatement.

An audit involves performing procedures to obtain audit evidence about the amounts and disclosures in the financial statements. The procedures selected depend on the auditor’s judgment, including the assessment of the risks of material misstatement of the financial statements, whether due to fraud or error. In making those risk assessments, the auditor considers internal control relevant to the entities’ preparation and fair presentation of the financial statements in order to design audit procedures that are appropriate in the circumstances, but not for the purpose of expressing an opinion on the effectiveness of the entity’s internal control. An audit also includes evaluating the appropriateness of accounting policies used and the reasonableness of accounting estimates made by management, as well as evaluating the overall presentation of the financial statements.

We believe that the audit evidence we have obtained is appropriate and sufficient to provide a basis for our audit opinion.

Opinion

In our opinion, the financial statements identified in the first paragraph present fairly, in all material respects, financial position of Hebei Elderly Care Development Project Financed by the Asian Development Bank as of December 31, 2019, its financial receipts and disbursements, the project implementation and the receipts and disbursements of special account for the year then ended in accordance with Chinese accounting standards and system, and the requirements of the project loan agreement.

Other Matter

We also examined the withdrawal application No.HB002 and the attached documents submitted to the ADB during the period. In our opinion, those documents comply with the project loan agreement and can serve as basis for loan withdrawal.

The audit report consists of the Auditor’s Opinion and two more parts hereinafter: Financial Statements and Notes to the Financial Statements, Audit Findings and Recommendations.

Hebei Provincial Audit Office of the People’s Republic of China

June 30, 2020

Address: No.195, South Youyi Street, Shijiazhuang City, Hebei Province,

P.R. China

Postcode: 050051

Tel.: 86-311-88606354

Fax: 86-311-88606120

The English translation is for the convenience of report users; Please take the Chinese audit report as the only official version.

二、财务报表及财务报表附注

Ⅱ. Financial Statements and Notes to the Financial Statements

（一）资金平衡表

i. Balance Sheet

资 金 平 衡 表

BALANCE SHEET

2019年12月31日

(As of December 31, 2019)

项目名称：亚洲开发银行贷款河北省养老服务体系建设项目

Project Name: Hebei Elderly Care Development Project Financed by the ADB

编报单位：河北省政府外债项目管理服务中心

Prepared by: Hebei Provincial Government Foreign Debt                               货币单位：人民币元

Project Management & Service Center                                                 Currency Unit: RMB Yuan

| 资 金 占 用 Application of Fund | 行次Line No. | 期初数 Beginning Balance | 期末数 Ending Balance | 资 金 来 源 Sources of Fund | 行次Line No. | 期初数 Beginning Balance | 期末数 Ending Balance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 一、项目支出合计 Total Project Expenditures | 1 | 4,656,982.58 | 44,268,177.48 | 一、项目拨款合计 Total Project Appropriation Funds | 28 | 7,415,062.31 | 45,086,800.60 |
| 1. 交付使用资产 Fixed Assets Transferred | 2 | - | - | 二、项目资本与项目资本公积 Project Capital and Capital Surplus | 29 | - | - |
| 2. 待核销项目支出 Construction Expenditures to be Disposed | 3 | - | - | 其中: 亚行赠款 ADB grant | 30 | - | - |
| 3. 转出投资 Investments Transferred-out | 4 | - | - | 三、项目借款合计 Total Project Loan | 31 | 69,933,869.36 | 74,558,501.87 |
| 4. 在建工程 Construction in Progress | 5 | 4,656,982.58 | 44,268,177.48 | 1. 项目投资借款 Total Project Investment Loan | 32 | 69,933,869.36 | 74,558,501.87 |
| 二、应收生产单位投资借款 Investment Loan Receivable | 6 | - | - | (1) 国外借款 Foreign Loan | 33 | 69,933,869.36 | 74,558,501.87 |
| 三、拨付所属投资借款 Appropriation of Investment Loan | 7 | - | - | 亚洲开发银行贷款Asian Development Bank Loan | 34 | 69,933,869.36 | 74,558,501.87 |
| 四、器材 Equipment | 8 | - | - | (2) 国内借款 Domestic Loan | 35 | - | - |
| 其中:待处理器材损失 Including: Equipment Losses in Suspense | 9 | - | - | 2. 其他借款 Other Loan | 36 | - | - |
| 五、货币资金合计 Total Cash and Bank | 10 | 69,292,723.12 | 79,411,143.35 | 四、上级拨入投资借款 Appropriation of Investment Loan | 37 | - | - |
| 1.银行存款 Cash in Bank | 11 | 69,292,723.12 | 79,411,143.35 | 五、企业债券资金 Bond Fund | 38 | - | - |
| 其中:专用账户存款 Including: Special Account | 12 | 68,731,949.40 | 70,746,567.22 | 六、待冲项目支出 Construction Expenditures to be Offset | 39 | - | - |
| 2. 现金 Cash on Hand | 13 | - | - | 七、应付款合计 Total Payable | 40 | 2,500,756.00 | 2,500,756.00 |
| 六、预付及应收款合计 Total Prepaid and Receivable | 14 | 6,000,000.00 | 183,398.17 | 其中：应付亚行贷款利息 Including: ADB Loan Interest Payable | 41 | - | - |
| 其中：应收亚行贷款利息 Including: ADB Loan Interest Receivable | 15 | - | - | 应付亚行贷款承诺费 Including: ADB Loan Commitment Fee Payable | 42 | - | - |
| 应收亚行贷款承诺费 Including:ADB Loan Commitment Fee Receivable | 16 | - | - | 八、未交款合计 Other Payables | 43 | 100,018.03 | 1,716,660.53 |

后续（To be continued）

续（continued）

| 资 金 占 用 Application of Fund | 行次Line No. | 期初数 Beginning Balance | 期末数 Ending Balance | 资 金 来 源 Sources of Fund | 行次Line No. | 期初数 Beginning Balance | 期末数 Ending Balance |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 七、有价证券 Marketable Securities | 17 | - | - | 九、上级拨入资金 Appropriation of Fund | 44 | - | - |
| 八、固定资产合计 Total Fixed Assets | 18 | - | - | 十、留成收入 Retained Earnings | 45 | - | - |
| 固定资产原价 Fixed Assets, Cost | 19 | - | - |  | 46 | - | - |
| 减:累计折旧 Less: Accumulated Depreciation | 20 | - | - |  | 47 | - | - |
| 固定资产净值 Fixed Assets, Net | 21 | - | - |  | 48 | - | - |
| 固定资产清理 Fixed Assets Pending Disposal | 22 | - | - |  | 49 | - | - |
| 待处理固定资产损失 Fixed Assets Losses in Suspense | 23 | - | - |  | 50 | - | - |
| 资金占用合计 Total Application of Fund | 24 | 79,949,705.70 | 123,862,719.00 | 资金来源合计 Total Sources of Fund | 51 | 79,949,705.70 | 123,862,719.00 |

（二）项目进度表

ii. Summary of Sources and Uses of Funds by Project Component

项 目 进 度 表（一）

SUMMARY OF SOURCES AND USES OF FUNDS

BY PROJECT COMPONENT Ⅰ

本期截至2019年12月31日

(For the period ended December 31, 2019）

项目名称：亚洲开发银行贷款河北省养老服务体系建设项目

Project Name: Hebei Elderly Care Development Project Financed by the ADB

编报单位：河北省政府外债项目管理服务中心                                                                   货币单位：人民币元

Prepared by:Hebei Provincial Government Foreign Debt Project Management & Service Center                              Currency Unit: RMB Yuan

| 项 目 内 容 Project Component | 本期 Current Period |  |  | 累计 Cumulative |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 本期计划额 Current Year Budget | 本期发生额 Current Period Actual | 本期完成比 Current Period % Completed | 项目总计划额 Life of PAD | 累计完成额 Cumulative Actual | 累计完成比 Cumulative % Completed |
| 资金来源合计 Total Sources of Funds | 47,173,586.00 | 42,296,370.80 | 89.66% | 1,148,120,000.00 | 119,645,302.47 | 10.42% |
| 一、亚洲开发银行贷款Asian Development Bank Loan | 11,423,586.00 | 4,624,632.51 | 40.48% | 665,000,000.00 | 74,558,501.87 | 11.21% |
| 二、配套资金Counterpart Fund | 35,750,000.00 | 37,671,738.29 | 105.38% | 483,120,000.00 | 45,086,800.60 | 9.33% |
| 1.财政拨款 Government | 7,710,000.00 | 7,760,000.00 | 100.65% | 156,221,000.00 | 9,060,000.00 | 5.80% |
| 2.企业自筹 Self-financed | 28,040,000.00 | 29,911,738.29 | 106.68% | 326,899,000.00 | 36,026,800.60 | 11.02% |
| 3.国债 State Bond | - | - | - | - | - | - |
| 4.国内借款 Domestic Loan | - | - | - | - | - | - |
| 三、赠款 Grant | - | - | - | - | - | - |
| 其中：亚行赠款 Asian Development Bank Grant | - | - | - | - | - | - |

后续（To be continued）

续（continued）

| 项 目 内 容 Project Component | 本期 Current Period |  |  | 累计 Cumulative |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 本期计划额 Current Year Budget | 本期发生额 Current Period Actual | 本期完成比 Current Period % Completed | 项目总计划额 Life of PAD | 累计完成额 Cumulative Actual | 累计完成比 Cumulative % Completed |
| 资金运用合计 Total Application of funds | 33,894,390.00 | 39,611,194.90 | 116.87% | 1,148,120,000.00 | 44,268,177.48 | 3.86% |
| 1.已交付使用资产Assets Transferred | - | - | - | - | - | - |
| 2.在建工程 Work in Progress | 33,894,390.00 | 39,611,194.90 | 116.87% | 1,148,120,000.00 | 44,268,177.48 | 3.86% |
| 1).建安工程投资 Investment in Construction and Installation Services and MIS | - | - | - | 576,701,700.00 | - |  |
| 2).设备投资 Investment of Equipment | - | - | - | 296,759,300.00 | - |  |
| 3).待摊投资 Prepaid Investment | 12,194,390.00 | 10,831,194.90 | 88.82% | 221,875,500.00 | 15,488,177.48 | 6.98% |
| 4).其他投资 Other Investment | 21,700,000.00 | 28,780,000.00 | 132.63% | 52,783,500.00 | 28,780,000.00 | 54.52% |
| 3.其他 Others | - | - | - | - | - | - |
| 差异 Difference | - | 2,685,175.90 | - | - | 75,377,124.99 | - |
| 1.应收账款变化 Change in Accounts Receivable | - | -5,816,601.83 | - | - | 183,398.17 | - |
| 2.应付账款变化 Change in Accounts Payable |  | - |  |  | -2,500,756.00 |  |
| 3.货币资金 Change in Cash and Bank |  | 10,118,420.23 |  |  | 79,411,143.35 |  |
| 4.其它 Other |  | -1,616,642.50 |  |  | -1,716,660.53 |  |

项 目 进 度 表（二）

SUMMARY OF SOURCES AND USES OF FUNDS

BY PROJECT COMPONENT Ⅱ

本期截至2019年12月31日

(For the period ended December 31, 2019）

项目名称：亚洲开发银行贷款河北省养老服务体系建设项目

Project Name: Hebei Elderly Care Development Project Financed by the ADB

编报单位：河北省政府外债项目管理服务中心                                                                                           货币单位：人民币元

Prepared by:Hebei Provincial Government Foreign Debt Project Management & Service Center                                  Currency Unit: RMB Yuan

| 项目内容 Project Component | 项目支出 Project Expenditure |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 累计支出 Cumulative Amount | 已交付资产 Assets Transferred |  |  |  | 在建工程 Work in Progress | 待核销项目支出Construction Expenditures to be Disposed | 转出投资Investments Transferred-out |
|  |  | 固定资产 Fixed Asset | 流动资产 Current Asset | 无形资产 Intangible Asset | 递延资产 Deferred Asset |  |  |  |
| 1.已交付使用资产Asset Transferred | - | - | - | - | - | - | - | - |
| 2.在建工程 Work in Progress | 44,268,177.48 | - | - | - | - | 44,268,177.48 | - | - |
| 1).建安工程投资 Investment in Construction and Installation | - | - | - | - | - | - | - | - |
| 2).设备投资 Investment of Equipment | - | - | - | - | - | - | - | - |
| 3).待摊投资 Prepaid Investment | 15,488,177.48 | - | - | - | - | 15,488,177.48 | - | - |
| 4).其他投资 Other Investment | 28,780,000.00 | - | - | - | - | 28,780,000.00 | - | - |
| 3. 其他 Others | - | - | - | - | - | - | - | - |
| 合计 Total | 44,268,177.48 | - | - | - | - | 44,268,177.48 | - | - |

（三）贷款协定执行情况表

iii. Statement of Implementation of Loan Agreement

贷 款 协 定 执 行 情 况 表

STATEMENT OF IMPLEMENTATION OF LOAN AGREEMENT

本期截至2019年12月31日

(For the period ended December 31, 2019）

项目名称：亚洲开发银行贷款河北省养老服务体系建设项目

Project Name: Hebei Elderly Care Development Project Financed by the ADB

编报单位：河北省政府外债项目管理服务中心                                                           货币单位：美元/人民币元

Prepared by:Hebei Provincial Government Foreign Debt Project Management & Service Center        Currency Unit: USD/ RMB Yuan

| 类 别 Category | 核定贷款金额 Loan Amount 美元 USD | 本年度提款数 Current-period Withdrawals |  | 累计提款数 Cumulative Withdrawals |  |
| --- | --- | --- | --- | --- | --- |
|  |  | 美元 USD | 折合人民币 RMB | 美元 USD | 折合人民币 RMB |
| 1.土建 Civil Works | 58,410,000.00 | - | - | - | - |
| 其中：巨鹿县 Julu County | 7,220,000.00 | - | - | - | - |
| 蠡县 Li County | 13,780,000.00 | - | - | - | - |
| 双滦区Chengde City,Shuangluan District | 11,570,000.00 | - | - | - | - |
| 渉县 She County | 6,960,000.00 | - | - | - | - |
| 辛集市 Xinji City | 8,800,000.00 | - | - | - | - |
| 燕山大学 Yanshan University | 10,080,000.00 | - | - | - | - |
| 2.货物 、能力提升及培训 Goods,Capacity Improvement and Training | 34,530,000.00 | 32,804.32 | 228,849.50 | 32,804.32 | 228,849.50 |
| 3.实施期利息和承诺费 Financial Charges during Implementation | 7,060,000.00 | 465,059.52 | 3,244,348.22 | 654,747.91 | 4,567,652.37 |
| 4.专用账户 Special Account | - | - | - | 10,000,000.00 | 69,762,000.00 |
| 总计 Total | 100,000,000.00 | 497,863.84 | 3,473,197.72 | 10,687,552.23 | 74,558,501.87 |

（四）专用账户报表

iv. Special Account Statement

专 用 账 户 报 表

SPECIAL ACCOUNT STATEMENT

本期截至2019年12月31日

(For the period ended December 31, 2019）

项目名称：亚洲开发银行贷款河北省养老服务体系建设项目

Project Name: Hebei Elderly Care Development Project Financed by the ADB贷款号：3536-PRC

Loan No.：3536-PRC

编报单位：河北省财政厅

Prepared by: The Finance Department of Hebei  Province

开户银行名称：中国建设银行股份有限公司石家庄桥西支行

Depository Bank: China Construction Bank Ltd. Shijiazhuang Qiaoxi Sub-branch

账号：13050161500800000970

Account No. : 13050161500800000970

货币种类：美元

Currency: USD

| A部分：本期专用账户收支情况 Part A-Account Activity for the Current Period | 金 额 Amount |
| --- | --- |
| 期初余额 Beginning Balance | 10,014,563.09 |
| 增加： Add: | - |
| 本期亚洲开发银行回补总额 Total Amount Deposited this Period by Asian Development Bank | - |
| 本期利息收入总额（存入专用账户部分） Total Interest Earned this Period if Deposited in Special Account | 231,500.78 |
| 本期不合格支出归还总额 Total Amount Refunded this Period to Cover Ineligible Expenditures | - |
| 减少： Deduct: | - |
| 本期支付总额 Total Amount Withdrawn this Period | 104,833.60 |
| 本期未包括在支付额中的服务费支出 Total Service Charges this Period if not Included in Above Amount Withdrawn | 97.96 |
| 期末余额 Ending Balance | 10,141,132.31 |

后续（To be continued）

续（continued）

| B部分：专用账户调节 Part B-Account Reconciliation |  | 金 额 Amount |
| --- | --- | --- |
| 1. 亚洲开发银行首次存款总额 Amount Advanced by Asian Development Bank |  | 10,000,000.00 |
| 减少： Deduct: |  | - |
| 2. 亚洲开发银行回收总额 Total Amount Recovered by Asian Development Bank |  | - |
| 3. 本期期末专用账户首次存款净额 Outstanding Amount Advanced to the Special Account at the End of this Period |  | 10,000,000.00 |
| 4. 专用账户期末余额 Ending Balance of Special Account |  | 10,141,132.31 |
| 增加： Add: |  | - |
| 5. 截至本期期末已申请报账但尚未回补金额 Amount Claimed but not yet Credited at the End of this Period |  |  |
| 申请书号 Application No. | 金额 Amount | - |
|  |  | - |
|  |  | - |
| 6. 截至本期期末已支付但尚未申请报账金额 Amount Withdrawn but not yet Claimed at the End of this Period |  | - |
| 7. 服务费累计支出（如未含在5和6栏中） Cumulative Service Charges (If not Included in Item 5 or 6) |  | 107.96 |
| 减少： Deduct: |  | - |
| 8. 利息收入（存入专用账户部分） Interest Earned (If Included in Special Account) |  | 246,073.87 |
| 9. 本期期末专用账户首次存款净额 Total Advance to the Special Account Accounted for at the End of this Period |  | 10,000,000.00 |

（五）财务报表附注

财务报表附注

1.项目概况

亚洲开发银行贷款河北省养老服务体系建设项目贷款号3536-PRC，旨在提高河北省养老服务体系能力和养老服务质量。本项目涉及6个子项目单位，主要项目内容包括提高社区和居家养老服务质量、提高机构养老服务能力和质量、开发人力资源，提升行业能力、养老行业组织能力提升。项目协议于2017年7月17日签订，2017年10月26日生效，预计于2022年6月30日完工，2022年12月31日关账。项目计划总投资为人民币1,148,120,000.00元，其中亚洲开发银行贷款总额为100,000,000.00美元，折合人民币665,000,000.00元，国内配套资金人民币483,120,000.00元。

2.财务报表编制范围

本财务报表的编制范围包括省项目办，燕山大学康养人才培训中心、辛集市养老服务中心（父母乐园）、承德市双滦区好人健康养老服务中心、保定蠡县养老综合服务中心、巨鹿县健康养老综合服务指导中心和涉县滨河老年颐养康复中心-润亲源养护院6个子项目的财务报表及省财政厅专用账户报表。

3.主要会计政策

3.1本项目财务报表按照财政部《世界银行贷款项目会计核算办法》（财际字〔2000〕13号）的要求编制。

3.2会计核算年度采用公历年制，即公历每年1月1日至12月31日。

3.3本项目会计核算以 “权责发生制”作为记账原则，采用借贷复式记账法记账，以人民币为记账本位币。

3.4 按照中国人民银行2019年12月31日汇率，即1美元=人民币6.9762元。

4.报表科目说明

4.1项目支出

2019年项目支出人民币39,611,194.90元，累计支出人民币44,268,177.48 元，占总投资计划的3.86%。

4.2货币资金

2019年12月31日货币资金余额为人民币79,411,143.35元，其中专用账户存款折合人民币70,746,567.22元。

4.3预付及应收款

2019年12月31日余额为人民币183,398.17元。

4.4项目拨款

2019年12月31日余额为人民币45,086,800.60元，是财政拨款及企业自筹到位的配套资金。

项目计划配套资金总额人民币483,120,000.00元，截至2019年12月31日到位配套人民币45,086,800.60元，占计划的9.33%，其中：财政拨款计划配套资金总额人民币156,221,000.00元，累计到位人民币9,060,000.00元，占计划的5.80%；企业自筹计划配套资金总额人民币326,899,000.00元，累计到位人民币36,026,800.60元，占计划的11.02%。

4.5项目借款

2019年12月31日余额为人民币74,558,501.87元，其中：亚洲开发银行贷款为10,687,552.23美元，折合人民币74,558,501.87元。

截至2019年12月31日，累计提取亚洲开发银行贷款资金10,687,552.23美元，占贷款总额的10.69%。其中：实施期利息和承诺费类累计提款654,747.91美元，占该类计划的9.27%。

4.6应付款

2019年12月31日余额为人民币2,500,756.00元，主要是应付巨鹿县医院垫付的土地划拨款。

4.7未交款

2019年12月31日余额为人民币1,716,660.53元，主要是专用账户利息收入。

5.专用账户使用情况

本项目专用账户设在中国建设银行股份有限公司石家庄桥西支行，账号为13050161500800000970，币种为美元。专用账户首次存款10,000,000.00美元。2019年年初余额 10,014,563.09美元，本年度回补0.00美元，利息收入231,500.78美元，本年度服务费支出97.96美元，年末余额10,141,132.31美元。

6.其他需要说明的事项

项目资金平衡表中亚洲开发银行贷款期末数与期初数之差、项目进度表中相应本期发生额与贷款协定执行情况表人民币本期提款数不一致是由于历年汇兑损益造成的。

- v. Notes to the Financial Statements

Notes to the Financial Statements

1.Project Overview

ADB Loan No. 3536-PRC of Hebei Elderly Care Development Project was aimed for the purpose of improving elderly care service system capacity and service quality in Hebei Province. The project is composed of 6 subprojects with main components including improving home and community-based care quality, enhancing capacity and quality of elderly care facilities, development of human capitals, sectoral and organizational capacities. The project agreement was signed on July 17, 2017 and took effective on October 26, 2017. It is expected to be completed on June 30, 2022 and closed on December 31, 2022. The project plans to invest RMB 1,148,120,000.00 yuan, of which ADB loan is USD 100,000,000.00 in total, equivalent to RMB 665,000,000.00 yuan and domestic counterpart fund is RMB 483,120,000.00 yuan.

2. Consolidation Scope of the Financial Statements

Consolidation scope of the financial statements covers the financial statements of provincial project office, Yanshan University Health and Elderly Care Integration Training Center, Xinji Parents' Paradise Elderly Care Community Center, Chengde Shuangluan District Haoren Health and Elderly Care Service Center Project, Baoding Li County Elderly Care Comprehensive Service Center, Julu County Healthcare and Elderly Care Integrated Service Center and She County Binhe Elderly Care and Rehabilitation Center- Runqinyuan Elderly Care Service as well as the Special Account set in the Provincial Financial Department.

3. Accounting Policies

3.1 The Financial Statements of the project were prepared according to the requirements of Accounting Methods for the World Bank Financed Project（Caijizi[2000]No.13）.

3.2 In accounting practice, the Gregorian calendar year is adopted as the fiscal year from January 1 to December 31.

3.3 The accrual basis and the debit/credit double entry bookkeeping method are adopted. RMB is used as the recording currency of bookkeeping.

3.4 The exchange rate adopted in the financial statements was the exchange rate on December 31, 2019 of the People’s Bank of China, which is USD 1= RMB 6.9762 yuan.

4. Explanation of Subjects

4.1 Total Project Expenditures

The project expenditure in 2019 was RMB 39,611,194.90 yuan and the cumulative expenditures were RMB 44,268,177.48 yuan, which accounted for 3.86% of the total investment plan.

4.2 Cash and Bank

On December 31, 2019, the balance was RMB 79,411,143.35 yuan. The funds in the Special Account were converted to RMB 70,746,567.22 yuan.

4.3 Prepaid and Receivable

Its balance on December 31, 2019 was RMB 183,398.17 yuan .

4.4 Project Appropriation Funds

The balance on December 31, 2019 was RMB 45,086,800.60 yuan, which was the counterpart funds by both financial budget and corporate own resources of fund-raising.

The total planned counterpart funds of this project were RMB 483,120,000.00 yuan. As of December 31, 2019, the counterpart fund of RMB 45,086,800.60 yuan was made available, which accounted for 9.33% of the plan. The total planned counterpart funds for financial budget were RMB 156,221,000.00 yuan and the actual cumulative allocated funds were RMB 9,060,000.00 yuan, 5.80% of the plan. The total planned counterpart funds for corporate self-raised were RMB 326,899,000.00 yuan and the actual cumulative allocated funds were RMB 36,026,800.60 yuan, 11.02% of the plan.

4.5 Project Loan

The balance on December 31, 2019 was RMB 74,558,501.87 yuan, including the ADB loan USD 10,687,552.23, equivalent to RMB 74,558,501.87 yuan.

As of December 31, 2019, accumulated USD 10,687,552.23 of the ADB loan had been withdrawn, accounting for 10.69% of the total, among which the withdrawal for financial charges during implementation was USD 654,747.91, accounting for 9.27% of the category plan.

4.6 Payable

The balance on December 31, 2019 was RMB 2,500,756.00 yuan, mainly paid for land transfer advanced by Julu county hospital.

4.7 Other Payables

The balance on December 31, 2019 was RMB 1,716,660.53 yuan, mainly the interest income of the Special Account.

5. Special Account

The Special Account of this project is set in China Construction Bank Ltd. Shijiazhuang Qiaoxi Sub-branch, with the account number of 13050161500800000970, and USD as currency Unit. The initial deposit of the Special Account is USD 10,000,000.00. The beginning balance of 2019 was USD 10,014,563.09 and the reimbursement in the year was USD 0.00. This year the interest earned was USD 231,500.78 and the service charges was USD 97.96. Thus, the ending balance was USD 10,141,132.31.

6. Other Explanation for the Financial Statements

Due to the change of foreign exchange rate, there are discrepancies between the difference of the beginning and ending balance of the ADB loan in the Balance Sheet, the cur	rent year’s loan received in the Summary of Sources and Uses of Funds by Project Component and the amount of current year’s withdrawals (disclosed in RMB) in the Statement of Implementation of Loan Agreement.

三、审计发现的问题及建议

审计发现的问题及建议

除对财务报表进行审计并发表审计意见外，审计中我们还关注了项目执行过程中相关单位国家法规和项目贷款协定遵守情况、内部控制和项目管理情况、项目绩效及上年度审计建议整改落实情况。我们认为，该项目将对构建具有河北特色的养老服务体系产生积极影响。我们发现存在如下问题：

项目管理方面存在的问题

1.蠡县子项目部分建设地点发生变更。

蠡县子项目10个日间照料中心中的9个建设地点发生了变更。建议你中心督促蠡县子项目加强计划管理和执行，推进日间照料中心建设顺利实施。你中心已接受审计建议。

2.辛集子项目部分管理费用支出管理不严。

辛集子项目在项目管理费用中列支3名借调人员2019年补贴,合计人民币47,160.00元。上述问题已于2020年6月15日整改完毕。建议你中心督促辛集子项目加强财务管理，避免发生类似问题。你中心已接受审计建议。

3.公司股东意见不同，导致承德子项目进展缓慢。

截至2019年12月31日，承德子项目累计完成额人民币983,282.90元，占该项目总计划的0.41%。主要原因是承德好人养老产业有限公司股东意见不同，影响了项目进展。该公司已完成股东调整工作。建议你中心督促承德子项目加快项目实施进度，保证项目顺利实施。你中心已接受审计建议。

- III. Audit Findings and Recommendations

Audit Findings and Recommendations

In addition to performing the audit and expressing an opinion on the financial statements, we also make observations with respect to compliance with applicable provisions of state laws and regulations and the loan agreement of the relevant entities, its internal financial control and project management， project performance and the follow-up of previous recommendations during the project implementing process. We think the project will have positive impacts on developing Hebei-specific elderly care service system. We found the following issues:

Issues on project management

1. Some construction sites of Li County Subproject had been changed

Nine of the ten Home and Community Based Care (HCBC) centers in the Li County Subproject had been changed construction sites. We suggested that your center urge Li County to strengthen plan management and implementation, and promote the smooth implementation of the construction of HCBC. Your center accepted the suggestion.

2. Some management expenditure of Xinji subproject was inadequate

Xinji subproject management expenditure listed three secondees' subsidy in 2019, totaling RMB 47,160.00 yuan. The above issue had been rectified on June 15, 2020. We suggested your center urge the Xinji subproject to strengthen financial management and avoid similar issues. Your center accepted the suggestion.

3. Slow progress of the Chengde subproject caused by different opinions among company's shareholders

As of December 31, 2019, the cumulative investment of the Chengde subproject was RMB 983,282.90 yuan, accounting for 0.41% of the plan. The main reason was that the shareholders of Chengde Haoren Elderly Care Industry Co., Ltd. had different opinions, which affected the progress of the project. The company had completed shareholder adjustment. We suggested your center urge Chengde subproject to speed up the project implementation progress and ensure the smooth implementation of the project. Your Center accepted the suggestion.